## BLANK ITIL Process Map (hidden)
RBQM PROJECT SPRINT
| PROJECT NAME |  |  | OVERALL PROGRESS | START DATE | END DATE | TOTAL DAYS |  | PROJECT DELIVERABLE
| Risk Based Quality Management tool |  |  | 0% | 2024-04-23 | 2024-09-30 | 160 |  | Graph database and visualization with drill/zoom feature.
| PROJECT MANAGER | [7 empty] | SCOPE STATEMENT
| Joseph Yoder | [7 empty] | Enhances overall study data information. Replacement for: Vision, Site Engagement, CDSO Scorecard, DSS KPI, HoS Dashboard, DBL Readiness, ALFA, RBQM, Patient Journey.
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DAYS | STATUS | STORY POINTS | STATUS KEY
| Sprint 1: Mock up Design |  |  |  | 2024-04-24 | 2024-05-06 | 13 | IN PROGRESS |  | COMPLETE
| Feature 1: Design for login page | Design | SriVishnu | 1 | 2024-04-25 | 2024-04-25 | 1 | COMPLETE | Design the Login Page | ON HOLD
| Feature 1: Design for home page | Design | SriVishnu | 1 | 2024-04-26 | 2024-04-26 | 1 | ON HOLD | Design the Home Page | IN PROGRESS
| Feature 2: Design for site monitor page | Design | SriVishnu |  | 2024-04-27 | 2024-04-29 | 3 | ON HOLD | KPI cards | OVERDUE
[8 empty] | OVERDUE | Filter/Search panel | NOT STARTED
[8 empty] | COMPLETE | Card view
|  | Design |  |  | 2024-04-29 | 2024-04-29 | 1 | COMPLETE | KRI Accordian view
|  | Design |  |  | 2024-04-30 | 2024-05-01 | 2 | IN PROGRESS | Study comparison view
|  | Design |  |  | 2024-05-02 | 2024-05-04 | 3 | IN PROGRESS | (i) buttons and other miscelleneous items
| Feature 4: Design for central monitor view | Design |  |  | 2024-05-06 | 2024-05-07 | 2 | ON HOLD
| Sprint 2: Development of login and landing page |  |  |  | 2024-05-07 | 2024-05-10 | 4 | NOT STARTED |  | NOT STARTED
| Feature 5: Creating the layout | Enigeering |  |  | 2024-05-07 | 2024-05-08 | 2 | NOT STARTED | All milestone dates at patient level. Key indicators for patient related information.
| Feature 6: Add functionality to site monitor card button | Interface |  |  | 2024-05-09 | 2024-05-09 | 1 | NOT STARTED | Layering the patient information. Developing user flow for roles interested in patient information.
| Feature 7: Central and site monitor cards with hover animations | Interface |  |  | 2024-05-10 | 2024-05-10 | 1 | NOT STARTED | Enhance feature to enable patient querying.
| Sprint 3: Development of skeletal site monitor page |  |  |  | 2024-05-10 | 2024-05-13 | 4 | NOT STARTED |  | NOT STARTED
| Feature 8: Creating the layout | Enigeering |  |  | 2024-05-10 | 2024-05-11 | 2 | NOT STARTED | Site: Site engagement data; RBQM data; ALFA data. Study: DBL risk values; QTL.
| Feature 9: Add home button, study number dropdown and search bar | Interface |  |  | 2024-05-12 | 2024-05-12 | 1 | NOT STARTED | Layering the study-level details. Layering the site-level details.
| Feature 10: Add functionality to the table view ,card view button and home button | Interface |  |  | 2024-05-13 | 2024-05-13 | 1 | NOT STARTED | Enhance feature to enable study and site detail querying.
| Sprint 4: Development of KPI cards and Card view |  |  |  | 2024-05-14 | 2024-05-17 | 4 | NOT STARTED |  | NOT STARTED
| Feature 11: Create the layout and add the respective terminologies with values | Enigeering |  |  | 2024-05-14 | 2024-05-14 | 1 | NOT STARTED | DSS KPI HoS Dashboard CDSO Scorecard DSS KPI
| Feature 12: Add d3 chart to the median KPI card | Interface |  |  | 2024-05-15 | 2024-05-15 | 1 | NOT STARTED | Layering in the details for each.
| Feature 13: Add a Search bar and create the layout of the cards view | Interface |  |  | 2024-05-16 | 2024-05-16 | 1 | NOT STARTED | Enhance feature to enable querying.
| Feature 14: Add all the informations as in design with buttons and d3 charts |  |  |  | 2024-05-17 | 2024-05-17 | 1 | NOT STARTED
| Sprint 5: Development of KRI Accordian and KRI Accordian compare view |  |  |  | 2024-05-17 | 2024-05-22 | 6 | NOT STARTED |  | NOT STARTED
| Feature 15: Add a table with list of comments card | Enigeering |  |  | 2024-05-17 | 2024-05-17 | 1 | NOT STARTED | RBQM - KRI/QTL ALFA
| Feature 16: Add d3 charts on the table | Interface |  |  | 2024-05-20 | 2024-05-22 | 3 | NOT STARTED | Layering in the details for each.
| Sprint 6: Backend data |  |  |  | 2024-05-16 | 2024-05-17 | 2 | NOT STARTED |  | NOT STARTED
| Feature 17: Create Nest App and connect to the server |  |  |  | 2024-05-16 | 2024-05-17 | 2 | NOT STARTED
NOT STARTED
NOT STARTED
| Sprint 7: Testing and Validation |  |  |  | 2024-10-02 | 2024-10-10 | 9 | NOT STARTED
NOT STARTED
NOT STARTED
NOT STARTED
Double-click Horizontal (Value) Axis to format Bound Minimum and Bound Maximum settings under Axis Options.* Delete any unpopulated rows in your table.*

## RBQM Sprint Plan (hidden)
RBQM PROJECT SPRINT
| PROJECT NAME |  |  | OVERALL PROGRESS | START DATE | END DATE | TOTAL DAYS |  | PROJECT DELIVERABLE
| Risk Based Quality Management tool |  |  |  | 2024-04-23 | 2024-06-30 | 68 |  | RBQM tool
| PROJECT MANAGER | [7 empty] | SCOPE STATEMENT
| Joseph Yoder |  |  |  | 4 |  |  |  | Enhances overall study data information. Replacement for: Vision, Site Engagement, CDSO Scorecard, DSS KPI, HoS Dashboard, DBL Readiness, ALFA, RBQM, Patient Journey.
| TASK NAME | FEATURE TYPE | RESPONSIBLE | # STORY POINTS | START | FINISH | DAYS | STATUS | STORY POINTS |  | STATUS KEY
Sprint 1: Mock up Design | Sprint 1: Mock up Design |  |  |  | 2024-04-24 | 2024-05-31 | 38 | IN PROGRESS |  | Sprint 1: Mock up Design | COMPLETE
Feature 1: Design for login pageDesign the Login Page | Feature 1: Design for login page | Design | SriVishnu | 1 | 2024-04-25 | 2024-04-25 | 1 | COMPLETE | Design the Login Page | Feature 1: Design for login pageDesign the Login Page | ON HOLD
Feature 2: Design for home pageDesign the Home Page | Feature 2: Design for home page | Design | SriVishnu | 1 | 2024-04-26 | 2024-04-26 | 1 | COMPLETE | Design the Home Page | Feature 2: Design for home pageDesign the Home Page | IN PROGRESS
Feature 3: Design for site monitor page KPI cards | Feature 3: Design for site monitor page | Design | SriVishnu | 6 | 2024-04-27 | 2024-05-20 | 24 | IN PROGRESS | KPI cards | Feature 3: Design for site monitor page KPI cards | OVERDUE
Filter/Search panel |  |  |  |  | 2024-04-27 | 2024-04-27 | 1 | COMPLETE | Filter/Search panel | Filter/Search panel | NOT STARTED
Card view |  |  |  |  | 2024-04-27 | 2024-05-20 | 24 | IN PROGRESS | Card view | Card view
KRI Accordian view |  |  |  |  | 2024-04-29 | 2024-04-29 | 1 | COMPLETE | KRI Accordian view | KRI Accordian view
Study comparison view |  |  |  |  | 2024-04-30 | 2024-05-01 | 2 | IN PROGRESS | Study comparison view | Study comparison view
(i) buttons and other miscelleneous items |  |  |  |  | 2024-05-02 | 2024-05-20 | 19 | NOT STARTED | (i) buttons and other miscelleneous items | (i) buttons and other miscelleneous items
Feature 4: Design for central monitor view | Feature 4: Design for central monitor view | Design | SriVishnu |  | 2024-05-20 | 2024-05-31 | 12 | ON HOLD |  | Feature 4: Design for central monitor view
Sprint 2: Development of login and landing page | Sprint 2: Development of login and landing page |  |  |  | 2024-05-08 | 2024-05-11 | 4 | COMPLETE |  | Sprint 2: Development of login and landing page
Feature 1: Develop the Login PageDevelop the login page | Feature 1: Develop the Login Page | Development | Thilaga | 1 | 2024-05-08 | 2024-05-08 | 1 | COMPLETE | Develop the login page | Feature 1: Develop the Login PageDevelop the login page
Feature 2: Develop Home PageDevelop the landing page with cards | Feature 2: Develop Home Page | Development | Akshara | 3 | 2024-05-09 | 2024-05-09 | 1 | COMPLETE | Develop the landing page with cards | Feature 2: Develop Home PageDevelop the landing page with cards
Add routing functionality |  |  |  |  | 2024-05-10 | 2024-05-10 | 1 | COMPLETE | Add routing functionality | Add routing functionality
Add Hover Animation |  |  |  |  | 2024-05-11 | 2024-05-11 | 1 | COMPLETE | Add Hover Animation | Add Hover Animation
Sprint 3: Development of Site Monitor page | Sprint 3: Development of Site Monitor page |  |  |  | 2024-05-12 | 2024-05-17 | 6 | IN PROGRESS |  | Sprint 3: Development of Site Monitor page
Feature 1: Developing the layoutDevelop Title Bar | Feature 1: Developing the layout | Development | Thilaga | 5 | 2024-05-12 | 2024-05-12 | 1 | COMPLETE | Develop Title Bar | Feature 1: Developing the layoutDevelop Title Bar
Develop Home button, Study dropdown |  |  |  |  | 2024-05-12 | 2024-05-12 | 1 | COMPLETE | Develop Home button, Study dropdown | Develop Home button, Study dropdown
Develop the placeholder KPI cards |  |  |  |  | 2024-05-12 | 2024-05-12 | 1 | COMPLETE | Develop the placeholder KPI cards | Develop the placeholder KPI cards
Add high risk toggle |  |  |  |  | 2024-05-12 | 2024-05-12 | 1 | COMPLETE | Add high risk toggle | Add high risk toggle
Search bar, dropdown filters for PI, Sort buttons, other functional buttons |  |  |  |  | 2024-05-12 | 2024-05-12 | 1 | COMPLETE | Search bar, dropdown filters for PI, Sort buttons, other functional buttons | Search bar, dropdown filters for PI, Sort buttons, other functional buttons
Feature 2: KPI PaneTBD | Feature 2: KPI Pane | [5 empty] | 1 | NOT STARTED | TBD | Feature 2: KPI PaneTBD
TBD | [6 empty] | 1 | NOT STARTED | TBD | TBD
TBD | [6 empty] | 1 | NOT STARTED | TBD | TBD
Feature 2: Developing the Card ViewStudy Number, PI Name, SiteName, Tier, Enrollment, Visits, Type of visit | Feature 2: Developing the Card View | Development | Akshara | 6 | 2024-05-13 | 2024-05-13 | 1 | COMPLETE | Study Number, PI Name, SiteName, Tier, Enrollment, Visits, Type of visit | Feature 2: Developing the Card ViewStudy Number, PI Name, SiteName, Tier, Enrollment, Visits, Type of visit
Gauge Chart (risk score) |  |  |  |  | 2024-05-14 | 2024-05-14 | 1 | COMPLETE | Gauge Chart (risk score) | Gauge Chart (risk score)
Summary of KRI signals |  |  |  |  | 2024-05-15 | 2024-05-15 | 1 | COMPLETE | Summary of KRI signals | Summary of KRI signals
Suggested Monitor Actions |  |  |  |  | 2024-05-15 | 2024-05-15 | 1 | COMPLETE | Suggested Monitor Actions | Suggested Monitor Actions
Study KRI details, Cross Study PI Risk buttons and ALFA signal |  |  |  |  | 2024-05-16 | 2024-05-16 | 1 | COMPLETE | Study KRI details, Cross Study PI Risk buttons and ALFA signal | Study KRI details, Cross Study PI Risk buttons and ALFA signal
Done for now, View Observations button |  |  |  |  | 2024-05-16 | 2024-05-16 | 1 | COMPLETE | Done for now, View Observations button | Done for now, View Observations button
KRI Details ViewRelevant KRI Observations card view | KRI Details View | Development | Thilaga | 5 |  |  | 1 | NOT STARTED | Relevant KRI Observations card view | KRI Details ViewRelevant KRI Observations card view
KRI table |  |  |  |  | 2024-05-17 | 2024-05-17 | 1 | COMPLETE | KRI table | KRI table
Red and Green triangles |  |  |  |  | 2024-05-17 | 2024-05-17 | 1 | COMPLETE | Red and Green triangles | Red and Green triangles
Compare View/KRI card View Toggle button |  |  |  |  | 2024-05-17 | 2024-05-17 | 1 | COMPLETE | Compare View/KRI card View Toggle button | Compare View/KRI card View Toggle button
KRI trend chart |  |  |  |  | 2024-05-17 | 2024-05-17 | 1 | IN PROGRESS | KRI trend chart | KRI trend chart
Compare ViewDropdown for Select Study | Compare View | Development | Akshara | 4 |  |  | 1 | NOT STARTED | Dropdown for Select Study | Compare ViewDropdown for Select Study
View Study level Avg toggle | [6 empty] | 1 | NOT STARTED | View Study level Avg toggle | View Study level Avg toggle
Heatmap chart | [6 empty] | 1 | NOT STARTED | Heatmap chart | Heatmap chart
Text inside Heatmap | [6 empty] | 1 | NOT STARTED | Text inside Heatmap | Text inside Heatmap
Aesthetics and Fine Tuning of UIResponsiveness of UI Layout | Aesthetics and Fine Tuning of UI | Development | Thilaga | 5 |  |  | 1 | NOT STARTED | Responsiveness of UI Layout | Aesthetics and Fine Tuning of UIResponsiveness of UI Layout
KPI Pane | [6 empty] | 1 | NOT STARTED | KPI Pane | KPI Pane
Card view | [6 empty] | 1 | NOT STARTED | Card view | Card view
KRI details view | [6 empty] | 1 | NOT STARTED | KRI details view | KRI details view
Compare view | [6 empty] | 1 | NOT STARTED | Compare view | Compare view
Double-click Horizontal (Value) Axis to format Bound Minimum and Bound Maximum settings under Axis Options.* Delete any unpopulated rows in your table.*

## RBQM Sprint Plan (2)
RBQM PROJECT SPRINT
| PROJECT NAME |  |  | OVERALL PROGRESS | START DATE | END DATE | TOTAL DAYS |  | PROJECT DELIVERABLE
| Risk Based Quality Management tool |  |  |  | 2024-04-23 | 2024-06-30 | 68 |  | RBQM tool
| PROJECT MANAGER | [7 empty] | SCOPE STATEMENT
| Joseph Yoder |  |  |  | 4 |  |  |  | Enhances overall study data information. Replacement for: Vision, Site Engagement, CDSO Scorecard, DSS KPI, HoS Dashboard, DBL Readiness, ALFA, RBQM, Patient Journey.
| TASK NAME | FEATURE TYPE | RESPONSIBLE | # STORY POINTS | START | FINISH | DAYS | STATUS | STORY POINTS |  | STATUS KEY
Sprint 1: Mock up Design | Sprint 1: Mock up Design |  |  |  | 2024-04-24 | 2024-05-31 | 38 | IN PROGRESS |  | Sprint 1: Mock up Design | COMPLETE
Feature 1: Design for login pageDesign the Login Page | Feature 1: Design for login page | Design | SriVishnu | 1 | 2024-04-25 | 2024-04-25 | 1 | COMPLETE | Design the Login Page | Feature 1: Design for login pageDesign the Login Page | ON HOLD
Feature 2: Design for home pageDesign the Home Page | Feature 2: Design for home page | Design | SriVishnu | 1 | 2024-04-26 | 2024-04-26 | 1 | COMPLETE | Design the Home Page | Feature 2: Design for home pageDesign the Home Page | IN PROGRESS
Feature 3: Design for site monitor page KPI cards | Feature 3: Design for site monitor page | Design | SriVishnu | 6 | 2024-04-27 | 2024-05-20 | 24 | COMPLETE | KPI cards | Feature 3: Design for site monitor page KPI cards | OVERDUE
Filter/Search panel |  |  |  |  | 2024-04-27 | 2024-04-27 | 1 | COMPLETE | Filter/Search panel | Filter/Search panel | NOT STARTED
Card view |  |  |  |  | 2024-04-27 | 2024-05-20 | 24 | COMPLETE | Card view | Card view
KRI Accordian view |  |  |  |  | 2024-04-29 | 2024-04-29 | 1 | COMPLETE | KRI Accordian view | KRI Accordian view
Study comparison view |  |  |  |  | 2024-04-30 | 2024-05-01 | 2 | COMPLETE | Study comparison view | Study comparison view
(i) buttons and other miscelleneous items |  |  |  |  | 2024-05-02 | 2024-05-20 | 19 | NOT STARTED | (i) buttons and other miscelleneous items | (i) buttons and other miscelleneous items
Feature 4: Design for central monitor view | Feature 4: Design for central monitor view | Design | SriVishnu |  | 2024-05-20 | 2024-05-31 | 12 | ON HOLD |  | Feature 4: Design for central monitor view
Sprint 2: Development of login and landing page and setting up Nest app | Sprint 2: Development of login and landing page and setting up Nest app |  |  |  | 2024-05-06 | 2024-05-17 | 12 | COMPLETE |  | Sprint 2: Development of login and landing page and setting up Nest app
| Feature 1: Develop the Login Page | Development | Thilaga | 2 | 2024-05-06 | 2024-05-06 | 1 | COMPLETE | Convert images into SVG format
[5 empty] | 2024-05-06 | 2024-05-06 | 1 | COMPLETE | Create basic structure of login page
Feature 2: Develop Home PageDevelop the landing page with cards | Feature 2: Develop Home Page | Development | Akshara | 3 | 2024-05-09 | 2024-05-09 | 1 | COMPLETE | Develop the landing page with cards | Feature 2: Develop Home PageDevelop the landing page with cards
Add routing functionality |  |  |  |  | 2024-05-10 | 2024-05-10 | 1 | COMPLETE | Add routing functionality | Add routing functionality
Add Hover Animation |  |  |  |  | 2024-05-11 | 2024-05-11 | 1 | COMPLETE | Add Hover Animation | Add Hover Animation
Feature 3: Setup Nest AppCreate a Nest app and install the necessary packages | Feature 3: Setup Nest App | Development | Akshara | 3 | 2024-05-08 | 2024-05-08 | 1 | COMPLETE | Create a Nest app and install the necessary packages | Feature 3: Setup Nest AppCreate a Nest app and install the necessary packages
[5 empty] | 2024-05-09 | 2024-05-09 | 1 | COMPLETE | Add credentials to connect the Nest app to the Oracle database
Check if any database can be fetchable |  |  |  |  | 2024-05-09 | 2024-05-09 | 1 | COMPLETE | Check if any database can be fetchable | Check if any database can be fetchable
Feature 4: Development of Site monitor page layoutDevelop the layout | Feature 4: Development of Site monitor page layout | Development | Akshara | 3 | 2024-05-10 | 2024-05-10 | 1 | COMPLETE | Develop the layout | Feature 4: Development of Site monitor page layoutDevelop the layout
Develop the KRI card layout |  |  |  |  | 2024-05-10 | 2024-05-10 | 1 | COMPLETE | Develop the KRI card layout | Develop the KRI card layout
Develop the Details card layout |  |  |  |  | 2024-05-10 | 2024-05-10 | 1 | COMPLETE | Develop the Details card layout | Develop the Details card layout
Sprint 3: Development of Site Monitor page | Sprint 3: Development of Site Monitor page |  |  |  | 2024-05-20 | 2024-05-31 | 12 | IN PROGRESS |  | Sprint 3: Development of Site Monitor page
Feature 1: Main study filterDevelop the main study filter with fucntionality | Feature 1: Main study filter | Development | Akshara | 2 |  |  | 1 | COMPLETE | Develop the main study filter with fucntionality | Feature 1: Main study filterDevelop the main study filter with fucntionality
Integrate the dummy data in the filter | [6 empty] | 1 | COMPLETE | Integrate the dummy data in the filter | Integrate the dummy data in the filter
Feature 2: Developing the main filter paneDevelop PI name dropdown filter | Feature 2: Developing the main filter pane | Development | Akshara | 4 |  |  | 1 | COMPLETE | Develop PI name dropdown filter | Feature 2: Developing the main filter paneDevelop PI name dropdown filter
Develop checkbox feature for multi select on PI name | [6 empty] | 1 | IN PROGRESS | Develop checkbox feature for multi select on PI name | Develop checkbox feature for multi select on PI name
Develop the sort by risk and sort by date functionality | [6 empty] | 1 | COMPLETE | Develop the sort by risk and sort by date functionality | Develop the sort by risk and sort by date functionality
Develop eye button with functionality | [6 empty] | 1 | COMPLETE | Develop eye button with functionality | Develop eye button with functionality
Feature 3: KPI PaneKPI card 1 - Site numbers | Feature 3: KPI Pane | [5 empty] | 1 | COMPLETE | KPI card 1 - Site numbers | Feature 3: KPI PaneKPI card 1 - Site numbers
KPI card 2 - Signalled site numbers |  | Development | Thilaga | 3 |  |  | 1 | COMPLETE | KPI card 2 - Signalled site numbers | KPI card 2 - Signalled site numbers
[8 empty] | COMPLETE | KPI card 3 - Observations
KPI card 3 - Observations | [6 empty] | 1 | COMPLETE | KPI card 4 - Median | KPI card 3 - Observations
Feature 4: Developing the Card ViewStudy Number, PI Name, SiteName, Tier, Enrollment, Visits, Type of visit | Feature 4: Developing the Card View | Development | Akshara | 6 |  |  | 1 | COMPLETE | Study Number, PI Name, SiteName, Tier, Enrollment, Visits, Type of visit | Feature 4: Developing the Card ViewStudy Number, PI Name, SiteName, Tier, Enrollment, Visits, Type of visit
Gauge Chart (risk score) | [6 empty] | 1 | COMPLETE | Gauge Chart (risk score) | Gauge Chart (risk score)
Summary of KRI signals | [6 empty] | 1 | COMPLETE | Summary of KRI signals | Summary of KRI signals
Suggested Monitor Actions | [6 empty] | 1 | COMPLETE | Suggested Monitor Actions | Suggested Monitor Actions
Study KRI details, Cross Study PI Risk buttons and ALFA signal | [6 empty] | 1 | COMPLETE | Study KRI details, Cross Study PI Risk buttons and ALFA signal | Study KRI details, Cross Study PI Risk buttons and ALFA signal
Done for now, View Observations button | [6 empty] | 1 | NOT STARTED | Done for now, View Observations button | Done for now, View Observations button
Feature 5: KRI Details ViewRelevant KRI Observations card view | Feature 5: KRI Details View | Development | Thilaga | 5 |  |  | 1 | IN PROGRESS | Relevant KRI Observations card view | Feature 5: KRI Details ViewRelevant KRI Observations card view
KRI table | [6 empty] | 1 | IN PROGRESS | KRI table | KRI table
Red and Green triangles | [6 empty] | 1 | IN PROGRESS | Red and Green triangles | Red and Green triangles
Compare View/KRI card View Toggle button | [6 empty] | 1 | COMPLETE | Compare View/KRI card View Toggle button | Compare View/KRI card View Toggle button
KRI trend chart | [6 empty] | 1 | IN PROGRESS | KRI trend chart | KRI trend chart
Sprint 4: | Sprint 4: |  |  |  | 2024-06-03 | 2024-06-14 | 12 |  |  | Sprint 4:
Feature 1: Search FunctionalityDevelop search bar with global search functionlity | Feature 1: Search Functionality | Development | Thilaga | 1 |  |  | 1 | COMPLETE | Develop search bar with global search functionlity | Feature 1: Search FunctionalityDevelop search bar with global search functionlity
Feature 2: Compare ViewDropdown for Select Study | Feature 2: Compare View | Development | Akshara | 4 |  |  | 1 | COMPLETE | Dropdown for Select Study | Feature 2: Compare ViewDropdown for Select Study
View Study level Avg toggle | [6 empty] | 1 | NOT STARTED | View Study level Avg toggle | View Study level Avg toggle
Heatmap chart | [6 empty] | 1 | IN PROGRESS | Heatmap chart | Heatmap chart
Text inside Heatmap | [6 empty] | 1 | IN PROGRESS | Text inside Heatmap | Text inside Heatmap
Feature 2: KRI popup Description viewDevelop a modal layout with close button for the popup | Feature 2: KRI popup Description view | Development | Akshara | 3 |  |  | 1 | NOT STARTED | Develop a modal layout with close button for the popup | Feature 2: KRI popup Description viewDevelop a modal layout with close button for the popup
Develop a trigger functionality on the detials button to popup | [6 empty] | 1 | NOT STARTED | Develop a trigger functionality on the detials button to popup | Develop a trigger functionality on the detials button to popup
Add the chart inside the modal with static data and legends | [6 empty] | 1 | NOT STARTED | Add the chart inside the modal with static data and legends | Add the chart inside the modal with static data and legends
Feature 3: Connect to databaseVerify and add the credentials to login into the database using Nerst App | Feature 3: Connect to database | Development | Thilaga | 3 |  |  | 1 | NOT STARTED | Verify and add the credentials to login into the database using Nerst App | Feature 3: Connect to databaseVerify and add the credentials to login into the database using Nerst App
Search for the table database | [6 empty] | 1 | NOT STARTED | Search for the table database | Search for the table database
Check for any specify column which we want to fetch | [6 empty] | 1 | NOT STARTED | Check for any specify column which we want to fetch | Check for any specify column which we want to fetch
Sprint 5: Aesthetics and API calling | Sprint 5: Aesthetics and API calling |  |  |  | 2024-06-17 | 2024-06-28 | 12 |  |  | Sprint 5: Aesthetics and API calling
Feature 1: Aesthetics and Fine Tuning of UIResponsiveness of UI Layout | Feature 1: Aesthetics and Fine Tuning of UI | Development | Thilaga | 5 |  |  | 1 |  | Responsiveness of UI Layout | Feature 1: Aesthetics and Fine Tuning of UIResponsiveness of UI Layout
KPI Pane | [6 empty] | 1 |  | KPI Pane | KPI Pane
Card view | [6 empty] | 1 |  | Card view | Card view
KRI details view | [6 empty] | 1 |  | KRI details view | KRI details view
Compare view | [6 empty] | 1 |  | Compare view | Compare view
Feature 2: Download as image feature Develop a functionality to download the entire card as image | Feature 2: Download as image feature | Development | Thilaga | 1 |  |  | 1 |  | Develop a functionality to download the entire card as image | Feature 2: Download as image feature Develop a functionality to download the entire card as image
Feature 3: Study numbers API | Feature 3: Study numbers API | Development | Akshara | 3 |  |  | 1 |  |  | Feature 3: Study numbers API
1
1
Feature 4: Number of sites and observations API | Feature 4: Number of sites and observations API | Development | Akshara | 3 |  |  | 1 |  |  | Feature 4: Number of sites and observations API
1
1
Feature 5: PI name and Medians API | Feature 5: PI name and Medians API | Development | Akshara | 3 |  |  | 1 |  |  | Feature 5: PI name and Medians API
1
1
Sprint 6: API Calling | Sprint 6: API Calling |  |  |  | 2024-07-01 | 2024-07-12 | 12 |  |  | Sprint 6: API Calling
Feature 1: Card API | Feature 1: Card API | Development | Thilaga | 1 |  |  | 1 |  |  | Feature 1: Card API
Feature 2: KRI Details API | Feature 2: KRI Details API | Development | Akshara | 3 |  |  | 1 |  |  | Feature 2: KRI Details API
1
1
Feature 3: Trend chart API | Feature 3: Trend chart API | Development | Akshara | 3 |  |  | 1 |  |  | Feature 3: Trend chart API
1
1
Feature 4: Last 3 months tasks/obeservations API | Feature 4: Last 3 months tasks/obeservations API | Development | Akshara | 3 |  |  | 1 |  |  | Feature 4: Last 3 months tasks/obeservations API
1
1
Sprint 7: | Sprint 7: |  |  |  | 2024-07-15 | 2024-07-26 | 12 |  |  | Sprint 7:
Feature 1: Compare view APIs | Feature 1: Compare view APIs | Development | Thilaga | 1 |  |  | 1 |  |  | Feature 1: Compare view APIs
Feature 2: Export as ppt functionality | Feature 2: Export as ppt functionality | Development | Akshara | 3 |  |  | 1 |  |  | Feature 2: Export as ppt functionality
1
1
Feature 3: Done for now functionality | Feature 3: Done for now functionality | Development | Akshara | 3 |  |  | 1 |  |  | Feature 3: Done for now functionality
1
1
Sprint 8: External links | Sprint 8: External links |  |  |  | 2024-07-29 | 2024-08-09 | 12 |  |  | Sprint 8: External links
Feature 1: View Observation functionalityDevelop a functionality to navigate to the Tesla observation site | Feature 1: View Observation functionality | Development | Thilaga | 1 |  |  | 1 |  | Develop a functionality to navigate to the Tesla observation site | Feature 1: View Observation functionalityDevelop a functionality to navigate to the Tesla observation site
Feature 2: ALFA link Trigger a fucntionality on the hyperlink to hover to the ALFA | Feature 2: ALFA link | Development | Akshara | 2 |  |  | 1 |  | Trigger a fucntionality on the hyperlink to hover to the ALFA | Feature 2: ALFA link Trigger a fucntionality on the hyperlink to hover to the ALFA
1
Double-click Horizontal (Value) Axis to format Bound Minimum and Bound Maximum settings under Axis Options.* Delete any unpopulated rows in your table.*

## RBQM Sprint Plan (3) (hidden)
RBQM PROJECT SPRINT
| PROJECT NAME |  |  | OVERALL PROGRESS | START DATE | END DATE | TOTAL DAYS |  | PROJECT DELIVERABLE
| Risk Based Quality Management tool |  |  |  | 2024-04-23 | 2024-06-30 | 68 |  | RBQM tool
| PROJECT MANAGER | [7 empty] | SCOPE STATEMENT
| Joseph Yoder |  |  |  | 4 |  |  |  | Enhances overall study data information. Replacement for: Vision, Site Engagement, CDSO Scorecard, DSS KPI, HoS Dashboard, DBL Readiness, ALFA, RBQM, Patient Journey.
| TASK NAME | FEATURE TYPE | RESPONSIBLE | # STORY POINTS | START | FINISH | DAYS | STATUS | STORY POINTS |  | STATUS KEY
Sprint 1: Mock up Design | Sprint 1: Mock up Design |  |  |  | 2024-04-24 | 2024-05-31 | 38 | IN PROGRESS |  | Sprint 1: Mock up Design | COMPLETE
Feature 1: Design for login pageDesign the Login Page | Feature 1: Design for login page | Design | SriVishnu | 1 | 2024-04-25 | 2024-04-25 | 1 | COMPLETE | Design the Login Page | Feature 1: Design for login pageDesign the Login Page | ON HOLD
Feature 2: Design for home pageDesign the Home Page | Feature 2: Design for home page | Design | SriVishnu | 1 | 2024-04-26 | 2024-04-26 | 1 | COMPLETE | Design the Home Page | Feature 2: Design for home pageDesign the Home Page | IN PROGRESS
Feature 3: Design for site monitor page KPI cards | Feature 3: Design for site monitor page | Design | SriVishnu | 6 | 2024-04-27 | 2024-05-20 | 24 | IN PROGRESS | KPI cards | Feature 3: Design for site monitor page KPI cards | OVERDUE
Filter/Search panel |  |  |  |  | 2024-04-27 | 2024-04-27 | 1 | COMPLETE | Filter/Search panel | Filter/Search panel | NOT STARTED
Card view |  |  |  |  | 2024-04-27 | 2024-05-20 | 24 | IN PROGRESS | Card view | Card view
KRI Accordian view |  |  |  |  | 2024-04-29 | 2024-04-29 | 1 | COMPLETE | KRI Accordian view | KRI Accordian view
Study comparison view |  |  |  |  | 2024-04-30 | 2024-05-01 | 2 | IN PROGRESS | Study comparison view | Study comparison view
(i) buttons and other miscelleneous items |  |  |  |  | 2024-05-02 | 2024-05-20 | 19 | NOT STARTED | (i) buttons and other miscelleneous items | (i) buttons and other miscelleneous items
Feature 4: Design for central monitor view | Feature 4: Design for central monitor view | Design | SriVishnu |  | 2024-05-20 | 2024-05-31 | 12 | ON HOLD |  | Feature 4: Design for central monitor view
Sprint 2: Development of login and landing page and setting up Nest app | Sprint 2: Development of login and landing page and setting up Nest app |  |  |  | 2024-05-06 | 2024-05-17 | 12 | COMPLETE |  | Sprint 2: Development of login and landing page and setting up Nest app
| Feature 1: Develop the Login Page | Development | Thilaga | 3 | 2024-05-06 | 2024-05-06 | 1 | COMPLETE | Convert images into SVG format
[5 empty] | 2024-05-06 | 2024-05-06 | 1 | COMPLETE | Create basic structure of login page
[5 empty] | 2024-05-06 | 2024-05-06 | 1 | COMPLETE | Add routing functionality to login page
#REF! | Feature 2: Develop Landing Page |  |  |  | 2024-05-07 | 2024-05-07 | 1 | COMPLETE | Develop a basic structure for landing page | #REF!
#REF! |  |  |  |  | 2024-05-07 | 2024-05-07 | 1 | COMPLETE | Add Hover Animation | #REF!
[5 empty] | 2024-05-07 | 2024-05-07 | 1 | COMPLETE | Add routing functionality to landing page
| Feature 3:Aesthetics |  |  |  | 2024-05-08 | 2024-05-08 | 1 | COMPLETE | Work on aesthatics of login page
[5 empty] | 2024-05-08 | 2024-05-08 | 1 | COMPLETE | Work on aesthatics of landing page
Feature 3: Setup Nest AppCreate a Nest app and install the necessary packages | Feature 3: Setup Nest App | Development | Akshara | 3 | 2024-05-08 | 2024-05-08 | 1 | COMPLETE | Create a Nest app and install the necessary packages | Feature 3: Setup Nest AppCreate a Nest app and install the necessary packages
[5 empty] | 2024-05-09 | 2024-05-08 | 0 | COMPLETE | Add credentials to connect the Nest app to the Oracle database
Check if any database can be fetchable |  |  |  |  | 2024-05-09 | 2024-05-09 | 1 | COMPLETE | Check if any database can be fetchable | Check if any database can be fetchable
[5 empty] | 2024-05-09 | 2024-05-09 | 1 | COMPLETE
Feature 4: Development of Site monitor page layoutDevelop the layout | Feature 4: Development of Site monitor page layout | Development | Akshara | 3 | 2024-05-10 | 2024-05-10 | 1 | COMPLETE | Convert icons and image into svg format | Feature 4: Development of Site monitor page layoutDevelop the layout
Develop the KPI card layout |  |  |  |  | 2024-05-10 | 2024-05-10 | 1 | COMPLETE | Develop the layout | Develop the KPI card layout
Develop the KRI card layout |  |  |  |  | 2024-05-10 | 2024-05-10 | 1 | COMPLETE | Develop the KPI card layout | Develop the KRI card layout
Develop the Search panel layout |  |  |  |  | 2024-05-13 | 2024-05-13 | 1 | COMPLETE | Develop the KRI card layout | Develop the Search panel layout
#REF! |  |  |  |  | 2024-05-13 | 2024-05-13 | 1 | COMPLETE | Develop the Search panel layout | #REF!
Give Spacing for the KRI card Layout |  |  |  |  | 2024-05-13 | 2024-05-13 | 1 | COMPLETE | Give the scroll function for the KRI layout | Give Spacing for the KRI card Layout
[5 empty] | 2024-05-14 | 2024-05-14 | 1 | COMPLETE | Give Spacing for the KRI card Layout
[5 empty] | 2024-05-14 | 2024-05-14 | 1 | COMPLETE | Insert icons and images in the layouts
[5 empty] | 2024-05-14 | 2024-05-14 | 1 | COMPLETE | Give the shadow effect for the KRI layout
[5 empty] | 2024-05-15 | 2024-05-15 |  | COMPLETE | Divide the KRI card layout to divisions
[5 empty] | 2024-05-15 | 2024-05-15 |  | COMPLETE | Divide the Search panel layout
[5 empty] | 2024-05-15 | 2024-05-15 |  | COMPLETE | Add icons to the search panel layout
[5 empty] | 2024-05-16 | 2024-05-16 |  | COMPLETE | Aesthetics of the Search panel Layout
[5 empty] | 2024-05-16 | 2024-05-16 |  | COMPLETE
[5 empty] | 2024-05-16 | 2024-05-16 |  | COMPLETE
[5 empty] | 2024-05-17 | 2024-05-17 |  | COMPLETE
[5 empty] | 2024-05-17 | 2024-05-17 |  | COMPLETE
[5 empty] | 2024-05-17 | 2024-05-17 |  | COMPLETE
Sprint 3: Development of Site Monitor page | Sprint 3: Development of Site Monitor page |  |  |  | 2024-05-20 | 2024-05-31 | 12 | IN PROGRESS |  | Sprint 3: Development of Site Monitor page
Feature 1: Main study filterDevelop the main study filter with fucntionality | Feature 1: Main study filter | Development | Akshara | 2 |  |  | 1 | NOT STARTED |  | Feature 1: Main study filterDevelop the main study filter with fucntionality
Integrate the dummy data in the filter | [6 empty] | 1 | NOT STARTED | Develop the main study filter with fucntionality | Integrate the dummy data in the filter
Feature 2: Developing the main filter paneDevelop PI name dropdown filter | Feature 2: Developing the main filter pane | Development | Akshara | 4 |  |  | 1 | COMPLETE | Integrate the dummy data in the filter | Feature 2: Developing the main filter paneDevelop PI name dropdown filter
Develop checkbox feature for multi select on PI name | [6 empty] | 1 | COMPLETE | Develop PI name dropdown filter | Develop checkbox feature for multi select on PI name
Develop the sort by risk and sort by date functionality | [6 empty] | 1 | COMPLETE | Develop checkbox feature for multi select on PI name | Develop the sort by risk and sort by date functionality
Develop eye button with functionality | [6 empty] | 1 | COMPLETE | Develop the sort by risk and sort by date functionality | Develop eye button with functionality
Feature 3: KPI PaneTBD | Feature 3: KPI Pane | [5 empty] | 1 | NOT STARTED | Develop eye button with functionality | Feature 3: KPI PaneTBD
TBD |  | Development | Thilaga | 3 |  |  | 1 | NOT STARTED | TBD | TBD
TBD | [6 empty] | 1 | NOT STARTED | TBD | TBD
Feature 4: Developing the Card ViewStudy Number, PI Name, SiteName, Tier, Enrollment, Visits, Type of visit | Feature 4: Developing the Card View | Development | Akshara | 6 |  |  | 1 | COMPLETE | TBD | Feature 4: Developing the Card ViewStudy Number, PI Name, SiteName, Tier, Enrollment, Visits, Type of visit
Gauge Chart (risk score) | [6 empty] | 1 | COMPLETE | Study Number, PI Name, SiteName, Tier, Enrollment, Visits, Type of visit | Gauge Chart (risk score)
Summary of KRI signals | [6 empty] | 1 | COMPLETE | Gauge Chart (risk score) | Summary of KRI signals
Suggested Monitor Actions | [6 empty] | 1 | COMPLETE | Summary of KRI signals | Suggested Monitor Actions
Study KRI details, Cross Study PI Risk buttons and ALFA signal | [6 empty] | 1 | COMPLETE | Suggested Monitor Actions | Study KRI details, Cross Study PI Risk buttons and ALFA signal
Done for now, View Observations button | [6 empty] | 1 | COMPLETE | Study KRI details, Cross Study PI Risk buttons and ALFA signal | Done for now, View Observations button
Feature 5: KRI Details ViewRelevant KRI Observations card view | Feature 5: KRI Details View | Development | Thilaga | 5 |  |  | 1 | NOT STARTED | Done for now, View Observations button | Feature 5: KRI Details ViewRelevant KRI Observations card view
KRI table | [6 empty] | 1 | COMPLETE | Relevant KRI Observations card view | KRI table
Red and Green triangles | [6 empty] | 1 | COMPLETE | KRI table | Red and Green triangles
Compare View/KRI card View Toggle button | [6 empty] | 1 | COMPLETE | Red and Green triangles | Compare View/KRI card View Toggle button
KRI trend chart | [6 empty] | 1 | IN PROGRESS | Compare View/KRI card View Toggle button | KRI trend chart
Sprint 4: | Sprint 4: |  |  |  | 2024-06-03 | 2024-06-14 | 12 | COMPLETE | KRI trend chart | Sprint 4:
Feature 1: Search FunctionalityDevelop search bar with global search functionlity | Feature 1: Search Functionality | Development | Thilaga | 1 |  |  | 1 | IN PROGRESS |  | Feature 1: Search FunctionalityDevelop search bar with global search functionlity
Feature 2: Compare ViewDropdown for Select Study | Feature 2: Compare View | Development | Akshara | 4 |  |  | 1 | NOT STARTED | Develop search bar with global search functionlity | Feature 2: Compare ViewDropdown for Select Study
View Study level Avg toggle | [6 empty] | 1 | NOT STARTED | Dropdown for Select Study | View Study level Avg toggle
Heatmap chart | [6 empty] | 1 | NOT STARTED | View Study level Avg toggle | Heatmap chart
Text inside Heatmap | [6 empty] | 1 | NOT STARTED | Heatmap chart | Text inside Heatmap
Feature 2: KRI popup Description viewDevelop a modal layout with close button for the popup | Feature 2: KRI popup Description view | Development | Akshara | 3 |  |  | 1 | COMPLETE | Text inside Heatmap | Feature 2: KRI popup Description viewDevelop a modal layout with close button for the popup
Develop a trigger functionality on the detials button to popup | [6 empty] | 1 | COMPLETE | Develop a modal layout with close button for the popup | Develop a trigger functionality on the detials button to popup
Add the chart inside the modal with static data and legends | [6 empty] | 1 | COMPLETE | Develop a trigger functionality on the detials button to popup | Add the chart inside the modal with static data and legends
Feature 3: Connect to databaseVerify and add the credentials to login into the database using Nerst App | Feature 3: Connect to database | Development | Thilaga | 3 |  |  | 1 | COMPLETE | Add the chart inside the modal with static data and legends | Feature 3: Connect to databaseVerify and add the credentials to login into the database using Nerst App
Search for the table database | [6 empty] | 1 | COMPLETE | Verify and add the credentials to login into the database using Nerst App | Search for the table database
Check for any specify column which we want to fetch | [6 empty] | 1 | COMPLETE | Search for the table database | Check for any specify column which we want to fetch
Sprint 5: Aesthetics and API calling | Sprint 5: Aesthetics and API calling |  |  |  | 2024-06-17 | 2024-06-28 | 12 | COMPLETE | Check for any specify column which we want to fetch | Sprint 5: Aesthetics and API calling
Feature 1: Aesthetics and Fine Tuning of UIResponsiveness of UI Layout | Feature 1: Aesthetics and Fine Tuning of UI | Development | Thilaga | 5 |  |  | 1 | NOT STARTED |  | Feature 1: Aesthetics and Fine Tuning of UIResponsiveness of UI Layout
KPI Pane | [6 empty] | 1 | NOT STARTED | Responsiveness of UI Layout | KPI Pane
Card view | [6 empty] | 1 | NOT STARTED | KPI Pane | Card view
KRI details view | [6 empty] | 1 | NOT STARTED | Card view | KRI details view
Compare view | [6 empty] | 1 | NOT STARTED | KRI details view | Compare view
Feature 2: Download as image feature Develop a functionality to download the entire card as image | Feature 2: Download as image feature | Development | Thilaga | 1 |  |  | 1 | COMPLETE | Compare view | Feature 2: Download as image feature Develop a functionality to download the entire card as image
Feature 3: Study numbers API | Feature 3: Study numbers API | Development | Akshara | 3 |  |  | 1 | COMPLETE | Develop a functionality to download the entire card as image | Feature 3: Study numbers API
[7 empty] | 1 | COMPLETE
[7 empty] | 1 | COMPLETE
Feature 4: Number of sites and observations API | Feature 4: Number of sites and observations API | Development | Akshara | 3 |  |  | 1 | COMPLETE |  | Feature 4: Number of sites and observations API
[7 empty] | 1 | COMPLETE
[7 empty] | 1 | COMPLETE
Feature 5: PI name and Medians API | Feature 5: PI name and Medians API | Development | Akshara | 3 |  |  | 1 | COMPLETE |  | Feature 5: PI name and Medians API
[7 empty] | 1 | COMPLETE
[7 empty] | 1 | COMPLETE
Sprint 6: API Calling | Sprint 6: API Calling |  |  |  | 2024-07-01 | 2024-07-12 | 12 | COMPLETE |  | Sprint 6: API Calling
Feature 1: Card API | Feature 1: Card API | Development | Thilaga | 1 |  |  | 1 | COMPLETE |  | Feature 1: Card API
Feature 2: KRI Details API | Feature 2: KRI Details API | Development | Akshara | 3 |  |  | 1 | COMPLETE |  | Feature 2: KRI Details API
[7 empty] | 1 | COMPLETE
[7 empty] | 1 | COMPLETE
Feature 3: Trend chart API | Feature 3: Trend chart API | Development | Akshara | 3 |  |  | 1 | COMPLETE |  | Feature 3: Trend chart API
[7 empty] | 1 | COMPLETE
[7 empty] | 1 | COMPLETE
Feature 4: Last 3 months tasks/obeservations API | Feature 4: Last 3 months tasks/obeservations API | Development | Akshara | 3 |  |  | 1 | COMPLETE |  | Feature 4: Last 3 months tasks/obeservations API
[7 empty] | 1 | COMPLETE
[7 empty] | 1 | COMPLETE
Sprint 7: | Sprint 7: |  |  |  | 2024-07-15 | 2024-07-26 | 12 | COMPLETE |  | Sprint 7:
Feature 1: Compare view APIsDevelop the login page | Feature 1: Compare view APIs | Development | Thilaga | 1 |  |  | 1 | COMPLETE |  | Feature 1: Compare view APIsDevelop the login page
Feature 2: Export as ppt functionalityDevelop a popup screen to export the entire cards in ppt format | Feature 2: Export as ppt functionality | Development | Akshara | 3 |  |  | 1 | COMPLETE | Develop the login page | Feature 2: Export as ppt functionalityDevelop a popup screen to export the entire cards in ppt format
Add the dowload functionality to the export button | [6 empty] | 1 | COMPLETE | Develop a popup screen to export the entire cards in ppt format | Add the dowload functionality to the export button
Check whether all the cards are there in ppt | [6 empty] | 1 | COMPLETE | Add the dowload functionality to the export button | Check whether all the cards are there in ppt
Feature 3: Done for now functionalityTrigger a functionality on done for now button to mark it as complete | Feature 3: Done for now functionality | Development | Akshara | 3 |  |  | 1 | COMPLETE | Check whether all the cards are there in ppt | Feature 3: Done for now functionalityTrigger a functionality on done for now button to mark it as complete
Make the Required actions dynamic wrt the done for now feature | [6 empty] | 1 | COMPLETE | Trigger a functionality on done for now button to mark it as complete | Make the Required actions dynamic wrt the done for now feature
Make the card to greyed out and disabled | [6 empty] | 1 | COMPLETE | Make the Required actions dynamic wrt the done for now feature | Make the card to greyed out and disabled
Sprint 8: External links | Sprint 8: External links |  |  |  | 2024-07-29 | 2024-08-09 | 12 | COMPLETE | Make the card to greyed out and disabled | Sprint 8: External links
Feature 1: View Observation functionalityDevelop a functionality to hover to the Tesla observation site | Feature 1: View Observation functionality | Development | Thilaga | 1 |  |  | 1 | COMPLETE |  | Feature 1: View Observation functionalityDevelop a functionality to hover to the Tesla observation site
Feature 2: ALFA link Trigger a fucntionality on the hyperlink to hover to the ALFA | Feature 2: ALFA link | Development | Akshara | 2 |  |  | 1 | COMPLETE | Develop a functionality to hover to the Tesla observation site | Feature 2: ALFA link Trigger a fucntionality on the hyperlink to hover to the ALFA
[7 empty] | 1 | COMPLETE | Trigger a fucntionality on the hyperlink to hover to the ALFA
Double-click Horizontal (Value) Axis to format Bound Minimum and Bound Maximum settings under Axis Options.* Delete any unpopulated rows in your table.*

## -Disclaimer- (hidden)
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.

## BLANK ITIL Process Map (2) (hidden)
RBQM PROJECT SPRINT
| PROJECT NAME |  |  | OVERALL PROGRESS | START DATE | END DATE | TOTAL DAYS |  | PROJECT DELIVERABLE
| Risk Based Quality Management tool |  |  | 0% | 2024-04-23 | 2024-09-30 | 160 |  | Graph database and visualization with drill/zoom feature.
| PROJECT MANAGER | [7 empty] | SCOPE STATEMENT
| Joseph Yoder | [7 empty] | Enhances overall study data information. Replacement for: Vision, Site Engagement, CDSO Scorecard, DSS KPI, HoS Dashboard, DBL Readiness, ALFA, RBQM, Patient Journey.
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DAYS | STATUS | STORY POINTS | STATUS KEY
| Sprint 1: Mock up Design |  |  |  | 2024-04-24 | 2024-05-06 | 13 | ON HOLD |  | COMPLETE
| Feature 1: Design for login page | Design |  | 1 | 2024-04-25 | 2024-04-25 | 1 | COMPLETE | Design the Login Page | ON HOLD
| Feature 1: Design for home page | Design |  | 1 | 2024-04-26 | 2024-04-26 | 1 | COMPLETE | Design the Home Page
| Feature 2: Design for site monitor page | Design |  |  | 2024-04-27 | 2024-04-29 | 3 | COMPLETE | Interactive feature that allows query of graphical database. | OVERDUE
| Feature 3.1: KPI card design | Design |  |  | 2024-04-29 | 2024-04-29 | 1 | COMPLETE
| Feature 3.2: Card view design | Design |  |  | 2024-04-30 | 2024-05-01 | 2 | COMPLETE
| Feature 3.3: KRI Accordian view design | Design |  |  | 2024-05-02 | 2024-05-04 | 3 | COMPLETE
| Feature 3.4: KRI Accordian compare view design | Design |  |  | 2024-05-04 | 2024-05-06 | 3 | COMPLETE
| Feature 4: Design for central monitor view | Design |  |  | 2024-05-06 | 2024-05-07 | 2 | COMPLETE
| Sprint 2: Development of login and landing page |  |  |  | 2024-05-07 | 2024-05-10 | 4 | COMPLETE |  | NOT STARTED
| Feature 5: Creating the layout | Enigeering |  |  | 2024-05-07 | 2024-05-08 | 2 | COMPLETE | All milestone dates at patient level. Key indicators for patient related information.
| Feature 6: Add functionality to site monitor card button | Interface |  |  | 2024-05-09 | 2024-05-09 | 1 | COMPLETE | Layering the patient information. Developing user flow for roles interested in patient information.
| Feature 7: Central and site monitor cards with hover animations | Interface |  |  | 2024-05-10 | 2024-05-10 | 1 | COMPLETE | Enhance feature to enable patient querying.
| Sprint 3: Development of skeletal site monitor page |  |  |  | 2024-05-10 | 2024-05-13 | 4 | COMPLETE |  | NOT STARTED
| Feature 8: Creating the layout | Enigeering |  |  | 2024-05-10 | 2024-05-11 | 2 | COMPLETE | Site: Site engagement data; RBQM data; ALFA data. Study: DBL risk values; QTL.
| Feature 9: Add home button, study number dropdown and search bar | Interface |  |  | 2024-05-12 | 2024-05-12 | 1 | COMPLETE | Layering the study-level details. Layering the site-level details.
| Feature 10: Add functionality to the table view ,card view button and home button | Interface |  |  | 2024-05-13 | 2024-05-13 | 1 | COMPLETE | Enhance feature to enable study and site detail querying.
| Sprint 4: Development of KPI cards and Card view |  |  |  | 2024-05-14 | 2024-05-17 | 4 | COMPLETE |  | NOT STARTED
| Feature 11: Create the layout and add the respective terminologies with values | Enigeering |  |  | 2024-05-14 | 2024-05-14 | 1 | COMPLETE | DSS KPI HoS Dashboard CDSO Scorecard DSS KPI
| Feature 12: Add d3 chart to the median KPI card | Interface |  |  | 2024-05-15 | 2024-05-15 | 1 | COMPLETE | Layering in the details for each.
| Feature 13: Add a Search bar and create the layout of the cards view | Interface |  |  | 2024-05-16 | 2024-05-16 | 1 | COMPLETE | Enhance feature to enable querying.
| Feature 14: Add all the informations as in design with buttons and d3 charts |  |  |  | 2024-05-17 | 2024-05-17 | 1 | COMPLETE
| Sprint 5: Development of KRI Accordian and KRI Accordian compare view |  |  |  | 2024-05-17 | 2024-05-22 | 6 | IN PROGRESS |  | NOT STARTED
| Feature 15: Add a table with list of comments card | Enigeering |  |  | 2024-05-17 | 2024-05-17 | 1 | COMPLETE | RBQM - KRI/QTL ALFA
| Feature 16: Add d3 charts on the table | Interface |  |  | 2024-05-20 | 2024-05-22 | 3 | IN PROGRESS | Layering in the details for each.
| Sprint 6: Backend data |  |  |  | 2024-05-16 | 2024-05-17 | 2 | COMPLETE |  | NOT STARTED
| Feature 17: Create Nest App and connect to the server |  |  |  | 2024-05-16 | 2024-05-17 | 2 | COMPLETE
| Sprint 7: Testing and Validation |  |  |  | 2024-10-02 | 2024-10-10 | 9
Double-click Horizontal (Value) Axis to format Bound Minimum and Bound Maximum settings under Axis Options.* Delete any unpopulated rows in your table.*